## Instructions
Grant Tracking Spreadsheet
From GrantsManager (grantsmanager.com/templates/grant-tracking-spreadsheet)
How to use
1. Replace the example rows on each tab with your own proposals, awards, and deadlines.
2. Blue text is for you to enter. Black cells with formulas calculate automatically; do not overwrite them.
3. Update Spent and Encumbered on the Awards tab monthly from your financial system.
4. Status columns use drop-down lists. Add rows by copying an existing row so formulas come with it.
What the flags mean
Burn status compares % of budget committed (spent plus encumbered) with % of the project period elapsed.
Spending ahead: spending is more than 10 points ahead of time elapsed.
Underspending: spending is more than 15 points behind time elapsed.
On pace: everything in between.
Deadlines due within 30 days are shaded amber; overdue items are shaded red.
This tracker is for planning. Your award terms and institutional records govern.

## Proposals
Sponsor | Mechanism | Title | PI | Internal deadline | Sponsor deadline | Requested (total) | Status | Days to sponsor deadline | Notes
NIH | R01 | Neural circuits of memory consolidation (renewal) | Chen | 2027-02-02 | 2027-03-16 | 2500000 | Drafting
NSF | CAREER | Adaptive sensing for coastal systems | Okafor | 2027-07-01 | 2027-07-22 | 600000 | Drafting
DoD | CDMRP | Biomarkers for early detection | Reyes | 2026-11-20 | 2026-12-04 | 1200000 | Internal review
Formulas:
Days to sponsor deadline = IF([Sponsor deadline]="","",[Sponsor deadline]-TODAY())

## Awards
Award number | Sponsor | Title | PI | Start date | End date | Total budget | Spent | Encumbered | Remaining | % committed (spent + encumbered) | % time elapsed | Burn status | Days to end
AW-2022-0041 | NIH | Neural circuits of memory consolidation | Chen | 2022-07-01 | 2027-06-30 | 1720000 | 655000 | 120000
AW-2024-0067 | NSF | Computational models of hippocampal replay | Chen | 2024-01-01 | 2026-12-31 | 825000 | 730000 | 40000
AW-2023-0052 | NIH | Attentional control in aging adults | Whitfield | 2023-11-01 | 2026-10-31 | 150000 | 139000 | 0
Formulas:
Days to end = IF([End date]="","",[End date]-TODAY())

## Deadlines
Item | Type | Award or proposal | Owner | Due date | Status | Days until due | Notes
Annual RPPR | Progress report | AW-2022-0041 | Chen | 2027-05-15 | Not started
Final RPPR and FFR | Closeout | AW-2023-0052 | Research admin | 2027-02-28 | Not started
IACUC protocol renewal | Compliance | AW-2022-0041 | Chen | 2026-11-30 | In progress
Effort certification | Compliance | All | Research admin | 2026-11-15 | Not started
Formulas:
Days until due = IF([Due date]="","",[Due date]-TODAY())